## Sheet1
Task | Status | Notes | Date Last Updated | Status Types
Task 1: Layout including footer and header that auto adjusts on zoom levels | Complete | Sm:mt-12 md:mt-14 lg:24 for its margins mayb | 01/30/2024 | Complete
Task 2: Home Page that auto adjusts on zoom levels | Complete | using max-width min-width on css to make it so | 01/30/2024 | In Development
Task 3: Login Modal | Complete | Backend part remaining | 2024-02-02 | Pending
Task 4: Register Modal | Complete | Backend part remaining | 2024-05-02
Task 5: Establish DB Env | Complete |  | 2024-06-02
Task 6: DB:Schema/ERD | Complete |  | 2024-06-02
Task 7:Create DB Tables | Complete |  | 2024-07-02
Task 8: Create Factory for dummy data | Complete |  | 2024-07-02
Task 9: Register Backend | Complete | not sure if this is complete yet, but it seems it is. Had an issue where modal wasn’t closing after form misinput | 02/15/2024
Task 11: Logout Backend | Complete |  | 02/16/2024
Task 12 :Login Backend | In Development |  | 02/16/2024
Task 13: | Pending
Task 14: | Pending
Task 15: | Pending
Task 16: | Pending
Task 17: | Pending
Task 18: